## Sheet1
Bug ID | Task | Title | Description | Steps | Priority | Status | Dev Comments
QA-001 | D8 | Sign-in ignores return link (?next=): deep links, invites and MFA return are lost | After the Auth0 callback, auth-provider.tsx:149 only rewrites the URL with history.replaceState. RootPage (app/page.tsx:23) still works out the destination for "/" and redirects there, overwriting returnTo. RedirectIfSignedIn (guards.tsx:166) also ignores next. | 1) Sign out 2) Open /app/calls/?call=<id>; you are sent to /login/?next=… 3) Sign in 4) You land on /app/, not the call. Same for a signed-out existing user opening /invite/?token=X (invite never accepted), and for /mfa → Set up two-factor (returns to /app/) | High | Closed | Still present. auth-provider.tsx:149 only replaceStates to returnTo while RootPage's useSessionGate('/') redirects over it (app/page.tsx:23). Fix: after the callback, router.replace(returnTo) and skip the root gate when a returnTo exists; make RedirectIfSignedIn (guards.tsx:166) honour ?next= (same-origin paths only).
QA-002 | D8 | Invite lost after email verification for a new invitee | RequireVerified sends the user to /verify-email/ without next (guards.tsx:42). verify-email/page.tsx:41 always goes to "/" after verification, so the invite page never comes back. | 1) New user opens /invite/?token=X 2) Signs up 3) Verifies email 4) Lands on /setup/workspace/ and the invite is not accepted | Normal | Closed | Still present. RequireVerified (guards.tsx:43) and session-gate send to bare routes.verifyEmail, and verify-email/page.tsx:33,41 go to /. Fix: carry withNext(current) into /verify-email and redirect to next after verification.
QA-003 | D8 | "Create an account" link on login drops ?next= | login/page.tsx:48 links to routes.signup without the query string. | 1) Open /login/?next=%2Finvite%2F%3Ftoken%3DX 2) Click "Create an account" 3) The /signup/ URL has no next | Low | Closed | Still present. login/page.tsx:48 <Link href={routes.signup}>. Fix: append the current ?next= to the signup link (and the reverse link on signup).
QA-004 | D8 / D9 | Workspace on onboarding_step 4 shows an endless loader on W5 | stepPath(4) points to /onboarding/test/, but the W5 guard needs step 5. The check 5 ≤ 4 fails, and the redirect target is the current page, so guards.tsx:116 shows the loader forever. ADR 0024 says step 4 should resume on W5. | 1) As owner, PATCH /workspace {"onboarding_step":4} 2) Open the portal 3) /onboarding/test/ spins forever | Normal | Closed | Still present. stepPath(4) → /onboarding/test/, but test/page.tsx guards step={5}; destination === pathname gives null redirect, so guards.tsx:116 loads forever. Fix: per ADR 0024, treat step 4 as 5 in the gate (allowed = step <= normalise(onboarding_step)), or migrate step-4 rows to 5.
QA-005 | D8 | Editor cannot get past W1 in a workspace that is still onboarding | PATCH /workspace is owner/admin only (workspaces.controller.ts:72). The 403 is swallowed (use-onboarding-agent.ts:48), and the W2 guard sends the editor back to W1. | 1) Invite a user as editor to a workspace on step 1 2) Sign in as that editor 3) Pick a template → Continue 4) The page returns to W1 | Normal | Closed | Still present. PATCH /workspace is @Roles('owner','admin') (workspaces.controller.ts:72), and use-onboarding-agent.ts:50 swallows the 403. Fix: either let editors advance onboarding_step (a separate route, editor+, forward-only) or show a "Ask an owner to continue setup" state instead of looping to W1.
QA-006 | D8 | W2 autosave cannot clear optional fields | An emptied field becomes undefined, and JSON drops it, so the server sees "unchanged" (use-brief-autosave.ts:104). The UI still shows "Saved". Affects agent_name, address, pricing, anything_else and never_do. | 1) W2 → clear "Agent name" 2) Wait for "Saved" 3) Reload 4) The old value is back | Normal | Closed | Still present. setValueAs turns '' into undefined, and diff() (use-brief-autosave.ts:104-111) puts undefined in the patch, which JSON drops. Fix: send null for cleared fields and make the draft PATCH treat null as "clear".
QA-007 | D8 | W2/W3 edits made just before leaving the page are lost | The debounced save is cancelled when the page unmounts (use-debounced.ts:40), and there is no beforeunload guard. W3 Continue stays enabled while a slider save is still pending. | 1) W2 → type in "About the business" 2) Within 1 s, click the Template stepper or reload 3) Come back: the text is gone | Normal | Closed | Still present. use-debounced.ts:40 cancels the pending save on unmount; no beforeunload on W2/W3; W3 Continue checks only state.saving, not the pending 600 ms saveTuning. Fix: flush (not cancel) on unmount, add beforeunload while dirty, disable Continue while a debounce is pending.
QA-008 | D8 | Invite tokens, Auth0 code/state and Stripe session_id sent to PostHog | posthog.tsx:124 sends the full window.location.href on every pageview, with no sanitising. | 1) Enable PostHog on staging 2) Open /invite/?token=X 3) PostHog → $pageview 4) $current_url contains token= | High | Closed | Still present, High (privacy). posthog.tsx:126 sends $current_url: window.location.href; no before_send/sanitize_properties; capture_pageleave also leaks. Fix: strip query and fragment (or allow-list params) for $current_url, $referrer and pageleave in a before_send hook.
QA-009 | D8 | W2 brief preview card has hard-coded English text | brief-card.tsx:70-81 has literal copy ("Answer questions about…", "Quote prices", "Claim to be human"…) that is not in en.json. | 1) W2 → add services, FAQs and a hand-off rule 2) The preview card shows untranslated text | Low | Closed | Still present. brief-card.tsx:70-81 derive()/label() build English literals. Fix: move them to en.json under wizard.w2.card.* with ICU plurals.
QA-010 | D8 | Other untranslated copy and error codes without a message | Hard-coded: ConfigMissing screen (guards.tsx:180), country names on A4 (countries.ts), the worker's reason (generate-panel.tsx:63). No en.json message for WORKSPACE_REQUIRED, AGENT_IN_USE, PUBLISH_IN_PROGRESS, INVALID_CURSOR. | 1) Open A4 workspace setup: the country list is English only 2) Delete an agent that is bound to a number: the server's English message is shown | Low | Closed | Still present. Hard-coded ConfigMissing (guards.tsx:180), English COUNTRIES names (countries.ts), raw generation.reason (generate-panel.tsx:63); en.json errors lack WORKSPACE_REQUIRED, AGENT_IN_USE, PUBLISH_IN_PROGRESS, INVALID_CURSOR. Fix: add keys; use Intl.DisplayNames for countries; map the worker reason to a code.
QA-011 | D8 | W3: making an "Also speaks" language the main language sends two saves at once | language-picker.tsx:34 fires two PATCH requests in parallel. The main language can revert, and Continue re-enables too early. | 1) W3 → add French (Canada) under "Also speaks" 2) Make it the main language 3) Reload 4) The main language may have reverted | Normal | Closed | Still present. language-picker.tsx:34-36 calls onPrimaryChange then onLanguagesChange, giving two parallel PATCH /draft (voice-settings.tsx:91-102). Fix: a single onChange({primary_language, languages}) and one save.
QA-012 | D8 | Root page spins forever when the workspaces request fails | session-gate.ts:44 treats an error as "ready, no destination", and app/page.tsx has no error screen or retry. | 1) Block GET /workspaces (500) 2) Sign in 3) / shows a spinner forever | Low | Closed | Still present. session-gate.ts:44,49 returns {ready:true, destination:null} on workspaces error; app/page.tsx only handles auth.error. Fix: an error state with a Retry button.
QA-013 | D8 | No way to switch workspace inside the wizard | WizardShell (wizard-shell.tsx:57) has no workspace switcher, and the user menu has no switch item. | 1) User with live workspace A and onboarding workspace B 2) Select B 3) No control to get back to A | Low | Closed | Still present. wizard-shell.tsx:57-66 has no switcher; user-menu.tsx:41-50 has none either. Fix: reuse the dashboard WorkspaceSwitcher in the wizard header or the user menu. Reopen:Fixed in the header only: frontend/web/src/components/wizard/wizard-shell.tsx:51 renders <WorkspaceSwitcher compact />. Still missing: frontend/web/src/components/shell/user-menu.tsx:22-58 (UserMenu) has only Theme, Language, Settings, Two-factor and Sign out, with no workspace entry. The original report named both places. On mobile, workspace-switcher.tsx:31 hides the name (compact ? 'hidden md:flex'), so only the initial is shown. Suggested fix: add a "Switch workspace" submenu to UserMenu, shown when the user has more than 1 membership, reusing the WorkspaceSwitcher list and switch logic, which also keeps ?next=. Add en.json and ar.json keys. If the product owner decides the header switcher is enough, close as accepted.
QA-014 | D8 | W3 analytics event sends the wrong step_no | use-onboarding-agent.ts:41 sends step − 1, and W3 advances to step 5, so step_no = 4 instead of 3. | 1) Complete W3 2) PostHog → onboarding_step_completed shows step_no 4 | Low | Closed | Still present. use-onboarding-agent.ts:41 sends step - 1; W3 calls advance(5), giving 4. Fix: pass the completed step explicitly (advance(next, 'voice', {completed: 3})) or map through ONBOARDING_STEPS.
QA-015 | D8 | W1: changing only the industry on the same template is not saved | template/page.tsx:79 never sends PATCH draft {industry} when the template is kept. | 1) Finish W1 with "dental" 2) Go back, keep the template, choose "restaurant" 3) Continue 4) W2 still shows dental | Low | Closed | Still present. template/page.tsx:79-80 keepExisting path only tracks and advances. Fix: when industry changed, PATCH /agents/:id/draft {industry} before advancing.
QA-016 | D8 | Invite for a different email shows a generic message | invite/page.tsx:59 replaces the server's specific message with the generic "invalid" text. | 1) Invite a@x.com 2) Open the invite signed in as b@x.com 3) A generic "invalid invite" message shows | Low | Closed | Still present. invite/page.tsx:59 maps every INVITE_INVALID to a generic string, hiding the wrong-email, expired and used messages (members.service.ts:285-289). Fix: give the server distinct codes (INVITE_WRONG_EMAIL, INVITE_EXPIRED, INVITE_USED) or show error.message.
QA-017 | D9 | Test call keeps running with no hang-up if the user leaves W5 during the mic prompt | use-test-call.ts:127 doesn't re-check that the page is still open after the mic prompt. The call starts on a closed page and is never disconnected, so it bills until the maximum duration. | 1) W5 → Start test call 2) While the mic prompt shows, click Continue 3) Allow the mic on W6 4) The agent talks on W6 with no hang-up | High | Closed | Still present, High (billing). use-test-call.ts:127-138 has no mounted.current check after getUserMedia; session.current is set after cleanup ran, so it's never disconnected. Fix: re-check mounted after every await; if unmounted, stop the tracks and don't create the call (or stopCall immediately).
QA-018 | D9 | W7 stops updating after a failed activation | use-activation.ts:35 stops polling and the live connection once an activation fails. A later activation that starts on its own is never shown. | 1) Delay the Stripe webhook 2) Pay, wait 90 s, click "Start going live": it fails 3) Re-enable the webhook 4) The page stays on "failed" | Normal | Closed | Still present. use-activation.ts:41,53 stops polling and SSE when failed. Fix: keep the SSE activation/agent topics subscribed after failure (or poll GET /agents/:id/activation slowly) so a new activation is picked up.
QA-019 | D9 | Unpaid checkout says "choose a pack below" but no pack selector shows for 90 s | activate/page.tsx:143 shows a "Confirming…" spinner until the 90 s patience runs out. :87 maps a refunded session to "Payment confirmed". | 1) Start checkout, don't pay 2) Open /onboarding/activate/?session_id=<id> 3) The message appears with no pack selector | Normal | Closed | Still present. activate/page.tsx:143 shows progress whenever returned, so abandoned shows "choose a pack below" with no PackageSelector until patienceOver (:190); :87 maps refunded → paid. Fix: render the selector immediately on abandoned/unpaid; map refunded to its own state.
QA-020 | D9 | A fast client clock hides the new activation on W7 | use-activation.ts:35 compares the browser clock with the server's created_at, allowing only 60 s of difference. | 1) Set the OS clock 3 min fast 2) Pay a pack 3) The page stays on "Confirming your payment…" | Low | Closed | Still present. use-activation.ts:35 compares server created_at with client since − 60 s. Fix: compare against a server timestamp (purchase.created_at or the checkout confirm response), not the browser clock.
QA-021 | D9 | Wrong error text on "Call again" while a version is still syncing | errors.ts:13 prefers the generic en.json text over the server's message, so "still being prepared" shows as "Tell us a bit more about the business…". | 1) W5 → submit Improve 2) Click "Call again" right away 3) The wrong text shows | Low | Closed | Still present. errors.ts:14-16 prefers en.json over the server message; BRIEF_INCOMPLETE from test-call.service.ts:110 shows as "Tell us a bit more…". Fix: give "version still syncing" its own code (e.g. VERSION_SYNCING) with copy, or prefer the server message for this code. Reopen:Fixed: test-call.service.ts:116 throws VERSION_SYNCING, and its message is in en.json:286. Still wrong: frontend/web/src/lib/errors.ts:15-17 always uses errors.<code> from en.json when the key exists, so the server's specific message for BRIEF_INCOMPLETE is never shown. Every case below displays en.json:250 instead: test-call.service.ts:67,72 "Generate the agent before testing it."; activation.service.ts:38 "Generate the agent before going live."; agent-publish.service.ts:78 "This agent has no version to publish yet."; agent-publish.service.ts:299 "Publish this agent before putting it back on the phone."; numbers.service.ts:186 "Publish that agent before pointing a number at it."; prompting.service.ts:131 "Generate the agent before giving feedback on it." Suggested fix: split the cases into their own codes (for example AGENT_NOT_GENERATED and AGENT_NOT_PUBLISHED), keeping BRIEF_INCOMPLETE for a brief that is really incomplete (prompting.service.ts:83,92). Add en.json and ar.json keys, update openapi/manifest.ts, and run openapi:generate.
QA-022 | D10 | Lint finding platform_named shows a raw i18n key | prompt-tab.tsx:234 looks up the rule's text, but en.json has no platform_named key. Also affects W2 "Edit the script". | 1) D3 → Advanced 2) Type the voice platform vendor's name 3) The raw key "dashboard.agents.prompt.rules.platform_named" shows | Normal | Closed | Still present. prompt-tab.tsx:234 renders rules.${rule}; en.json:1284-1295 lacks platform_named (emitted by lint.ts:57,186). Fix: add the key and fall back to a generic label for unknown rules.
QA-023 | D10 | Greeting/Closing cannot be cleared in the Advanced editor | prompt-tab.tsx:116 leaves out empty values, and the server falls back to the previous version's text (agents.service.ts:416, 434). | 1) D3 → Advanced 2) Empty "Closing" 3) Save 4) The new version still has the old closing | Normal | Closed | Still present. prompt-tab.tsx:116 omits empty greeting/closing; agents.service.ts:417,435 ?? falls back to base. Fix: send null/'' explicitly and treat it as a clear on the server (or block empty with validation if a greeting is mandatory).
QA-024 | D10 | Unsaved Advanced edits lost on a tab or menu switch, without warning | detail/page.tsx:108 unmounts the editor when the tab changes. In-app navigation does not trigger beforeunload. | 1) D3 → Advanced → type 2) Click the Voice tab 3) Come back: the edits are gone, with no warning | Normal | Closed | Still present. detail/page.tsx:109 unmounts PromptTab on tab change; no onDirtyChange passed, no guard in setTab (:51). Fix: keep PromptTab mounted (hidden) like W2 does, or confirm before switching tab or route when dirty.
QA-025 | D10 | Publish bar publishes the saved draft while the editor has unsaved edits | The PublishBar on the Advanced tab (detail/page.tsx:114) doesn't know about unsaved editor changes. | 1) Advanced → edit without saving 2) Click Publish 3) The pre-edit text goes live | Normal | Closed | Still present. detail/page.tsx:117 PublishBar takes no dirty state (publish-bar.tsx:19). Fix: lift dirty state and disable Publish (or prompt "Save first") while the editor has unsaved edits.
QA-026 | D10 | No sort or select-all for calls on mobile | Sort headers exist only in the desktop table (calls-table.tsx:58). The mobile cards have no sort control and no select-all. | 1) 390 px → /app/calls 2) There is no way to sort or select all | Low | Closed | Still present. calls-table.tsx:58-72 sort and select-all are desktop-only; calls-filters.tsx has no sort. Fix: add a sort select and a "Select all" to the mobile card header or filter bar.
QA-027 | D10 | Stats day windows off by an hour around DST | calls.query.service.ts:452 uses today's UTC offset for past midnights, so D1 disagrees with D2. | 1) Timezone America/Toronto, after 1 Nov 2026 2) Compare the D1 30-day total with D2 range=30d 3) The counts differ | Low | Closed | Still present. calls.query.service.ts:452-465 startOfLocalDay applies today's offset to past midnights. Fix: compute each day's midnight with the zone's offset on that date (Temporal/date-fns-tz zonedTimeToUtc).
QA-028 | D10 | "Handled at" and version date use the browser's timezone | call-drawer.tsx:220 and versions-tab.tsx:285 don't use the workspace timezone. | 1) Set the browser timezone different from the workspace's 2) Mark a call handled 3) The times don't line up | Low | Closed | Still present. call-drawer.tsx:220 and versions-tab.tsx:285 call formatDateTime without timeZone. Fix: pass the workspace timezone like the neighbouring calls (:161, :166/:218).
QA-029 | D11 | Toasts cover the mobile bottom tab bar | toaster.tsx:12 places toasts bottom-right with a small offset, on top of the tab bar. | 1) 390 px → Numbers → Routing → Save 2) The toast covers the tabs, which can't be tapped | Normal | Closed | Still present. toaster.tsx:12 bottom-right, no offset; the tab bar is fixed bottom-0 z-40. Fix: on mobile use position="top-center" or an offset of tab-bar height + safe-area.
QA-030 | D11 | More sheet stays open when you pick the page you're on | portal-shell.tsx:102 closes the sheet only when the path changes. | 1) 390 px → /app/settings/?tab=team 2) More → Settings 3) The sheet stays open and the tab behind it switches | Low | Closed | Still present. portal-shell.tsx:102 closes More only on pathname change; the Links (136-143) have no onClick. Fix: onClick={() => setMoreOpen(false)} on each sheet link.
QA-031 | D11 | Extra live-update (/events) connections opened under /app | use-generation.ts:67, use-after-call.ts:88 and use-feedback.ts:57 each open their own /events stream. ADR 0019 §1 says one. | 1) DevTools → filter "events" 2) D3 → Test tab → place a test call 3) A second /events request appears | Low | Closed | Still present. use-generation.ts:67, use-after-call.ts:88, use-feedback.ts:57 each useWorkspaceEvents → subscribeEvents (api-client events.ts:41). Fix: under /app, consume DashboardLiveProvider's stream (register topic listeners) instead of opening new ones (ADR 0019 §1).
QA-032 | D11 | Audit log missing details; staff actions untranslated and unfilterable | audit-view.ts has no mapping for role-change from/to, auto top-up details or staff actions, so they show as "System" in English. | 1) Change a member's role → Audit log: no details 2) Staff comp credits: "Credits · adjusted" / System, with no area filter | Low | Closed | Still present. audit-view.ts:65-99 lacks from/to, top-up meta, reason_code; AUDIT_AREAS lacks staff areas (credits, purchase); null actor shows "System" (audit-tab.tsx:49). Fix: add the mappings and keys; show "Support team" when meta.by='staff'.
QA-033 | D12 | Any staff role can see call recording URLs and transcripts via webhook events | admin-webhooks.service.ts:86 returns the raw payload, and the route has no staff-role restriction. This bypasses can_listen_recordings and leaves no audit row. | 1) Sign in as read-only staff 2) System → Webhooks 3) Open a call_ended event 4) recording_url and the transcript are visible | High | Closed | Still present, High (security). admin-webhooks.service.ts:86 returns the raw payloadJson; GET list/:id in admin.controllers.ts:544-552 have no @StaffRoles and no can_listen_recordings check. Fix: redact recording URLs and transcript unless the staff member has can_listen_recordings, add @StaffRoles, audit payload views.
QA-034 | D12 | Agent and number pause/resume skip role limits and the support-ticket rule | admin-agents.service.ts:76 and admin-numbers.service.ts:90 never check can_pause_tenant. The tenant pause does. | 1) Support staff, no ticket 2) Telephony → Numbers → Pause 3) Returns 200; expected 403 STAFF_LIMIT_EXCEEDED | High | Closed | Still present, High (permissions). admin-agents.service.ts:76 pause/resume and admin-numbers.service.ts:90 setPaused skip limits.assertCan(staff,'can_pause_tenant') and the support-ticket rule. Fix: apply the same checks as tenant pause (admin-customers.service.ts:427,491).
QA-035 | D12 / D13 | Flag save does not require a reason; "Other" accepted without a note | In adminUpsertFlagRequest (admin.ts:541) reason_code is optional and there is no note rule. The console pre-selects a reason. | 1) PUT /admin/flags/x {"default_on":true} with no reason: 200 2) Pick "Other" with an empty note: it saves | Normal | Closed | Still present. admin.ts:540 reason_code optional, no note refine for 'other'; console pre-selects testing_internal (flags-tab.tsx:219). Fix: make it required plus the standard other→note refine, empty default, Save disabled until valid.
QA-036 | D12 | Portal shows old pricing for more than 60 s after publish | Portal pricing queries cache for 5 minutes (wallet-sections.tsx:48 plus 5 other places). | 1) Portal → Wallet 2) Admin publishes a new price 3) Navigate away and back: the old price is still shown | Normal | Closed | Still present. useGetPricing(..., {staleTime: 5*60_000}) at wallet-sections.tsx:48,134,294 and 6 other places; nothing invalidates it. Fix: staleTime ≤ 60 s (one shared hook/constant) to meet the 60 s SLA.
QA-037 | D12 | Daily credit-adjust cap can be exceeded by parallel requests | staff-limits.service.ts:129 sums the last 24 h without a lock, and the wallet lock is per workspace. | 1) Support staff with daily cap N 2) Adjust customers A and B at the same moment, 0.6×N each 3) Both succeed | Normal | Closed | Still present. staff-limits.service.ts:129-135 sums 24 h of adjustments with no lock, called before withWallet (admin-customers.service.ts:583/592). Fix: a per-staff advisory lock (pg_advisory_xact_lock(hash(staff_id))) around check + insert in one transaction.
QA-038 | D12 | Job discard removes the queue job before recording, and swallows a removal failure | admin-jobs.service.ts:197 removes the job first and only logs errors; the audit row comes after. | 1) Discard a waiting job while the worker is busy 2) The job still runs, or no audit row is written | Normal | Closed | Still present. admin-jobs.service.ts:197-204 removes the queue job first, .catch only logs, audit at 211-235. Fix: record job.discard_requested in the tx, then remove; on failure write job.discard_failed and return an error instead of success.
QA-039 | D12 | Pricing publish/rollback/draft discard have no reason code | The pricing publish and rollback requests have no reason_code (admin.ts:683-698). The draft and cost audit rows are written outside the transaction. | 1) Publish pricing 2) SA14 → pricing.published has no reason | Normal | Closed | Still present. adminPricingPublishRequest / adminPricingRollbackRequest (admin.ts:683-698) have no reason_code; saveDraft (:103), discardDraft (:121) and saveCosts (:511) audit outside a tx. Fix: add staffActionRequest to these, write the audit in the same transaction.
QA-040 | D12 | Rollback skips publish safety checks; a failed rollback leaves orphan versions | admin-pricing.service.ts:393 doesn't check for recently bought packs or the margin floor, and inserts a new version on every attempt. | 1) Publish v2 with pack X, buy X 2) Roll back to v1: X is removed without error 3) With Stripe failing, roll back twice: 2 orphan versions | Normal | Closed | Still present. Rollback (admin-pricing.service.ts:393-474) skips preview() blockers (recent packs, margin floor) and inserts a new version each attempt. Fix: run the publish checks; reuse the pending version via pendingOrNewVersion on retry.
QA-041 | D12 / D13 | Reason dialogs open with a reason already selected | staff-action-dialog.tsx:46 defaults to customer_request; view-as, kill switch, flag delete and credits also pre-select one. | 1) Customer → View as 2) Click Start straight away 3) It succeeds with support_investigation | Normal | Closed | Still present. staff-action-dialog.tsx:47 defaults customer_request; view-as support_investigation (customer-header.tsx:131), kill switch service_issue (flags-tab.tsx:115,128), flags testing_internal (:196,219), credits goodwill (adjust-credits-dialog.tsx:23). Fix: start empty, require an explicit choice.
QA-042 | D12 | Lock user doesn't record a failed session revoke | admin-users.service.ts:125 swallows the revoke error, and the audit row shows only the block outcome. | 1) Remove delete:sessions from the M2M app 2) Lock a user 3) SA14 shows no failure | Low | Closed | Still present. admin-users.service.ts:125-129 swallows the revokeSessions error and still writes sessionsRevokedAt; audit after is only {locked, provider} (:140). Fix: record user.lock_provider_failed (like force-logout) and include the provider outcome.
QA-043 | D12 | Staff-paused draft agent cannot be resumed | admin-agents.service.ts:88 lets staff pause a draft agent, but resume refuses one that was never published (:138). | 1) Telephony → Agents → pause an unpublished agent 2) Resume → 409 | Low | Closed | Still present. Pause allows drafts (admin-agents.service.ts:88); resume refuses publishedVersion === null (:138-143). Fix: either refuse pausing an unpublished agent, or allow resume to restore the previous status.
QA-044 | D13 | Refund dialog treats the cap as per refund; the server checks it per purchase | refund-dialog.tsx:40 uses min(refundable, cap), while staff-limits.service.ts:151 adds what is already refunded. | 1) Finance (cap $2,000), $3,000 purchase 2) Refund $1,500 3) Refund $1,500 again: 403 | Normal | Closed | Still present. refund-dialog.tsx:40 max = min(refundable, cap), labelled "per-refund" (:47,:96); server checks already refunded + in-flight + amount (staff-limits.service.ts:159). Fix: max = min(refundable, cap − refunded − in_flight), copy says "per purchase".
QA-045 | D13 | Calls/Numbers search matches unrelated rows when the query has a digit | admin-calls.service.ts:31 and admin-numbers.service.ts:44 match phone numbers on the query's digits alone. | 1) /calls/ → search "Dental 1" 2) Unrelated calls appear | Normal | Closed | Still present. admin-calls.service.ts:31-32 and admin-numbers.service.ts:44-46 match phone numbers on any digits in q. Fix: only do the phone match when q is mostly digits (e.g. ≥ 4 digits and no letters).
QA-046 | D13 | New flag key allows "." and "-" in the console, but the API rejects them | The flags-tab.tsx:224 regex is looser than admin-flags.service.ts:96. | 1) System → Flags → Add, key "web.widget" 2) Save → 422 | Low | Closed | Still present. flags-tab.tsx:224 /^[a-z][a-z0-9_.-]{1,63}$/ vs API /^[a-z][a-z0-9_]{1,63}$/ (admin-flags.service.ts:96). Fix: share one regex from @portal/schemas.
QA-047 | D13 | Telephony Agents search says "customer" but doesn't search by customer | telephony/page.tsx:112 placeholder vs admin-agents.service.ts:52, which searches name and ids only. | 1) Telephony → Agents 2) Search a customer's name 3) No results | Low | Closed | Still present. Placeholder "Agent name, customer…" (telephony/page.tsx:112), but the search only covers name and ids (admin-agents.service.ts:52-57). Fix: add tenant name to the where clause, or change the placeholder.
QA-048 | D13 | Permission ticked in SA13 enables the button, but the API still returns 403 | permissions.ts checks only role limits; the API also checks staff roles. | 1) Tick Finance → "Publish pricing" 2) As Finance → Publish 3) 403 FORBIDDEN_ROLE | Low | Closed | Still present. permissions.ts:43-44 checks only role limits, while publish/rollback/edit are @StaffRoles(super_admin) (admin.controllers.ts:109-110,644,664). Fix: UI checks both the role matrix and the limits, or derive the role list from the manifest.
QA-049 | D13 | Canned responses cannot be managed; the picker never shows on a fresh DB | There is no create/delete UI and no seed data, and the picker shows only when the list is non-empty. | 1) Open a ticket on staging 2) There is no canned-response picker | Normal | Closed | Still present. Only useAdminListCannedResponses is used (ticket-sheet.tsx:259); create/delete hooks exist (endpoints.ts:126,135) unused; no seed; picker hidden when empty (:286). Fix: add a management UI (SA4 settings) plus seed defaults; show an empty-state link to manage.
QA-050 | D13 | View-as note allows 1,000 characters; the API limit is 500 | staff-action-dialog.tsx:138 vs admin.ts:722. | 1) View as → paste a 600-character note 2) Submit → 422 | Low | Closed | Still present. staff-action-dialog.tsx:138 maxLength={1000} vs adminImpersonateRequest.note.max(500) (admin.ts:726). Fix: take the max from the schema (one constant).
QA-051 | D13 | Minor admin copy/UX issues | The Refund-call macro says "once per ticket" but it's once per call; two Needs-attention links open the wrong filter; Telephony tabs keep the search; Change role with no change closes silently; the counter shows "N / 0" with no limit set. | 1) Overview → "Overdue number rentals": the filter doesn't match the count 2) Search Numbers, switch to Agents: the search carries over | Low | Closed | a) macro-dialogs.tsx:104 says "once per ticket", server is per call (admin-support.service.ts:776): fix the copy. b) kpi-cards.tsx:101 overdue rentals → customers?status=at_risk, :100 pending purchases → unfiltered: point to the right filters. c) telephony/page.tsx:41 doesn't clear q on tab change. d) Partly fixed: hint added (members-tab.tsx:245), but confirm isn't disabled and the dialog closes silently: disable confirm when the role is unchanged. e) admin-kpis.service.ts:350 allowance ?? 0 → "N / 0" (kpi-cards.tsx:77, health-strip.tsx:64): show "N live" when no limit is set.
QA-052 | D9 | W5 test call fails: "We could not start the test call" (503 UPSTREAM_UNAVAILABLE) | POST /agents/:id/test/web returns 503. Draft sync succeeded; the voice platform refused create-web-call (test-call.service.ts:131-134). Our request shape is valid for retell-sdk 6.0.1 (v3 endpoint). Likely config/account: platform API key, account balance/concurrency, or stack config. Real cause only in API log "test call refused upstream: …". | 1) app-staging → W5 (draft v2, 20 credits) 2) Call again, allow mic 3) Network: test/web = 503, message "We could not start the test call just now" 4) Check API log | High | Open | No change in createWebCall or SDK versions in 98f1af9..ed8502b. Needs the staging API log line to classify (401 = key, 402/balance = platform account, 404/422 = stack/sync, 5xx = platform outage)
QA-053 | D12/D13 | SA5 rollback note: console allows 1,000 chars, API limit 500 (regression) | versions.tsx:70 moved rollback onto StaffActionDialog without noteMax; adminPricingRollbackRequest.note is .max(500) (admin.ts:741). Old dialog had maxLength 500. | 1) SA5 → Versions → Roll back 2) Reason + 600-char note + ROLLBACK 3) 422 VALIDATION_FAILED | Low | Open | Fix: pass noteMax={500} like customer-header.tsx:130
QA-054 | D13 | SA5 Costs Save enabled for a role without "Edit pricing draft" → 403 | permissions.ts:68 editCosts checks role only; server asserts can_edit_pricing_draft (admin-pricing.service.ts:538). | 1) SA13 → untick "Edit pricing draft" for finance 2) As finance → SA5 → Costs → Save 3) 403 STAFF_LIMIT_EXCEEDED | Low | Open | Remainder of QA-048; add limit check to editCosts
QA-055 | D13 | Reopening a webhook payload within 5 min writes no second audit row | webhooks-table.tsx:114 staleTime: Infinity + 5-min client cache; stored body served without a request, so webhook.payload_viewed logged once per cache window, not per view. | 1) SA12 → Webhooks → open X 2) Close, reopen X within 5 min 3) No GET, one audit row | Low | Open | Set gcTime: 0 or invalidate on sheet close
QA-056 | D8 | W2/W3 pending autosave lost when switching workspace within the debounce window | useSwitchWorkspace sets the new workspace before navigating (workspace-switcher.tsx:31-34); unmount flush sends the PATCH with the new X-Workspace-Id and it fails as not found. | 1) W2 → type 2) Within 1.5 s switch workspace in header 3) PATCH fails; edit lost | Normal | Open | Flush before select(id), or capture workspace id at debounce time
QA-057 | D8 | W2 Continue / Generate proceed after a failed autosave | save() swallows the error (use-brief-autosave.ts:74); flush() resolves; Continue advances, Generate runs on the stale brief; isDirty false in error state so no leave warning. | 1) Make draft PATCH fail (5xx/offline) 2) Click Continue 3) Page moves on; fields dropped silently | Normal | Open | Rethrow from save() / block next() and generate() while state = error
QA-058 | D8 | API still lets owner/admin rewind onboarding step via PATCH /workspace | workspaces.service.ts:168 writes onboarding_step unconditionally; the new POST route is forward-only but the old field is not. Portal never sends it. | 1) PATCH /workspace {"onboarding_step":1} as owner 2) Step rewinds | Low | Open | Drop onboarding_step from the PATCH schema or make it conditional
QA-059 | D8 | W1 "existing agent" alert shows English template name in Arabic | template/page.tsx:120 uses raw API name instead of copy.templateName. | 1) Portal in Arabic 2) W1 with existing agent 3) English name in alert | Low | Open | Use useServerCopy().templateName
QA-060 | D8 | Invite accept error reveals the invited email to the wrong account (API only) | members.service.ts:376-379 puts the invited address in the INVITE_WRONG_EMAIL message; preview route withholds it. Portal shows its own copy. | 1) As b@x.com POST /invites/<token for a@x.com>/accept 2) Message contains a@x.com | Low | Open | Match the preview route's wording
QA-061 | D9 | W7 shows an old failed activation and hides the confirm error when checkout confirm fails | On any confirm error since → null (activate/page.tsx:101), so the latest activation (even an old failure) is shown; confirm error alert only renders with no activation; Check again unreachable. | 1) Agent with earlier failed activation 2) Return to /onboarding/activate/?session_id= while confirm returns 503 3) Old failure shown, no confirm error | Normal | Open | Remainder of QA-018; keep since = 'pending' on error and show the confirm error + Check again
QA-062 | D11 | Inviting an existing member tells the inviter "You are already a member" | errors.ALREADY_MEMBER (en.json:260, ar.json) worded for the invitee; server throws it only from POST /invites meaning the invited person is already a member. | 1) Settings → Team 2) Invite a current member's email 3) Wrong sentence | Low | Open | Reword key to "That person is already a member of this workspace."
QA-063 | D11 | Dead invite link stays on screen after Resend | Resend replaces row and token, but the original InviteCard keeps showing the old link; two boxes, first fails with INVITE_INVALID. | 1) Invite a@x.com 2) Pending invites → Resend → confirm 3) Both links shown; first dead | Low | Open | Clear InviteCard on resend
QA-064 | D11 | dir="auto" missing on nickname / ticket subject / member name / audit actor | ADR 0026 rule not applied at numbers-list.tsx:46, number-detail.tsx:92, support-tickets.tsx:182, team-tab.tsx:75, audit-tab.tsx:45. | 1) Portal in Arabic 2) Arabic nickname on a number 3) Left-aligned in list/detail | Low | Open | Add dir="auto" to those five spans
QA-065 | D13 | Staff name can't be corrected in the console; account menu shows the wrong name | The admin account menu shows "Prateek" for padmavathi@metacognixion.com (Super admin). The name comes from the Staff invite and is not updated from the Google account at sign-in. The Staff page has no way to edit a name, so a wrong name stays until someone changes the database. Expected: a super admin can edit a staff member's name in Staff, or the name defaults to the Google profile name when the invite had none. | 1. admin-staging.oraly.ai → sign in as padmavathi@metacognixion.com. 2. Click the avatar (top right): name shows "Prateek". 3. Staff → the row for padmavathi@metacognixion.com. 4. Try to edit the name: no option. | Low | Open | The name is staff_users.name, set only by the invite (admin-staff.service.ts:116-121, body.name). Binding on first sign-in (auth.guard.ts:104-112) writes authProviderId only. PATCH /admin/staff/:id already accepts name (admin-staff.service.ts, if (body.name !== undefined) data.name = body.name), but members-tab.tsx only calls update for active (line 276) and role. Fix: add "Edit name" to the Staff row actions using the existing PATCH (audited as staff.updated). Optional: when binding an invite with no name, fill it from the staff token's name claim. Data fix for staging: set padmavathi@metacognixion.com's name to "Padmavathi".
QA-066 | D12 | Webhooks table overflows: Replay button cut off at laptop width | On System → Webhooks the table is wider than the page. The last column (Replay) is clipped at the right edge, so the button shows as "Repl" and only works after a sideways scroll inside the table. The Queue column is "–" for every processed event but still takes space. Expected: the table fits a 1366 px window with Replay fully visible; sideways scroll only on narrow screens. | 1. admin-staging → System → Webhooks, window about 1366 px wide. 2. Look at the right edge: Replay is clipped. 3. Scroll inside the table to reach it. | Low | Open | webhooks-table.tsx:62-96 has 9 columns, several with fixed widths (whitespace-nowrap date with seconds, badges, a max-w-56 error cell, the copyable external id), and the DataTable wrapper is overflow-x-auto (common/data-table.tsx:49), so the overflow becomes a scrollbar. Fix: drop seconds from the date, or hide lower-value columns below xl (className: 'hidden xl:table-cell' on Provider, Queue, Error), let the Customer name wrap, and keep Replay as a sticky last column or move it into a row menu. Check the Jobs tab and the Customer 360 webhooks tab, which use the same table.
QA-067 | D12 | Health cards show "No detail" for a healthy check | On System → Health every OK card shows "No detail" under the service name. It reads as if information is missing, when it only means nothing is wrong. Expected: a healthy card shows nothing on that line, or "Healthy"; "No detail" only when the check cannot report (e.g. "not configured"). | 1. admin-staging → System → Health. 2. All 9 cards are OK. 3. Each shows "No detail". | Low | Open | health-cards.tsx:20 renders check.detail ?? 'No detail'; the API sends detail: null on an OK check (admin-system.service.ts:73,96,135,151,201). Fix: render nothing (or "Healthy") when signal === 'ok' && !detail, and keep "No detail" only for unknown.
QA-068 | D12 | Overview "Median time to live" is shown in raw minutes ("37,098 min") | The funnel footer shows "Median time to live 37,098 min". That is about 26 days and is hard to read as minutes. Expected: a human duration ("25.8 days" / "3 h 20 min"). | 1. admin-staging → Overview, 30d. 2. Funnel footer shows "37,098 min". | Low | Open | The API returns median_minutes_to_live as a number (admin-kpis.service.ts:251-256); the overview renders it with a fixed "min" suffix. Format through a duration helper in frontend/admin/src/lib/format.ts (days when ≥ 1440, hours when ≥ 60). The median of 2 values is the upper one (Math.floor(n/2)); fine for display, but with a small cohort consider showing the cohort size beside it.
QA-069 | D13 | Ticket assignee name is cut off ("Padmav…") | In the ticket panel the Assignee box is too narrow, so the name is truncated to "Padmav…" and the full name is visible only on hover. Expected: the full name, or the first name with the email on hover. | 1. admin-staging → Support → open ticket #1. 2. Assignee shows "Padmav…" next to Unassign. | Low | Open | ticket-sheet.tsx:175-184: the Assignee cell shares one row with the Status and Priority selects, and the name is truncate beside the button. Give the Assignee cell more room (sm:col-span-2, or stack the button under the name), and add title={t.assignee.email} on the span.
QA-070 | D11 | Audit log shows common.role.viewer instead of "Viewer" | In Settings → Audit log, rows for "Invited someone", "Joined the workspace" and role changes show the role as a raw key: Role: common.role.viewer. Expected: "Role: Viewer" (and Editor / Admin / Owner). Seen on both workspaces; the browser console logs MISSING_MESSAGE: common.role.viewer (en). | 1. app-staging → Settings → Audit log. 2. Find "Invited someone" or "Joined the workspace". 3. Details show Role: common.role.viewer. | Low | Open | src/dashboard/audit-view.ts:147 builds valueKey = common.role.${value}, and audit-tab.tsx:62 renders it with tc(valueKey). The role names are not under common in en.json/ar.json; they are shell.role.* (en.json:103, used by the user menu). Fix: use shell.role.${value} (or add common.role.* to both message files) and update audit-view.test.ts:56-57, which asserts the wrong key. messages.test.ts cannot catch this because the key is built at runtime; consider a test that resolves every valueKey the view can produce.
QA-071 | D12 | "Could not load" card for a missing record offers a useless Retry | On admin-staging, opening a customer with an unknown id shows "Could not load — That record does not exist (or was deleted)" with a Retry button. Retry cannot help for a record that does not exist. Expected: no Retry; a "Back to customers" link instead. | 1. admin-staging → open /customers/detail/?id=not-a-uuid. 2. Card shows the not-found message with Retry. 3. Click Retry: same card. | Low | Open | customers/detail/page.tsx:37 renders LoadError with onRetry for every error. For a 404 (isApiError(error, 'NOT_FOUND')) render the message with a link to routes.customers and no retry; same for the user and ticket detail pages.
QA-072 | D12 | Admin pages take 4–5 s to settle on every navigation | Every admin page (list and detail) takes 4–5.5 s before it is fully loaded, measured on 59 screens. Each page issues three API calls plus the 30-second health poll. Not a failure, but the console feels slow. Expected: a page is usable within ~1–2 s; shared data (/admin/me, health) should not be refetched on every navigation. | 1. admin-staging → click between Overview, Customers, Users, System. 2. Each page shows a loader for several seconds. 3. DevTools → Network: me, system/health and the page's own call on every navigation. | Low | Open | Crawl timings: 4.2–5.5 s per page with networkidle. /admin/me and /admin/system/health are refetched per page; give useAdminMe a long staleTime and let HealthStrip keep its 30 s poll without an initial refetch on route change (health-strip.tsx:17). Check whether the page's own list call waits for me to resolve first (serial instead of parallel).
QA-073 | D10 | Test tab says "Nothing is live yet" on an agent that is live or paused | The Test tab card says "You are testing draft version 5. Nothing is live yet." while the header shows "Live v2 · Draft v5". The sentence is only right before the first publish. Expected: "You are testing draft v5. Callers still hear live v2 until you publish." and, when paused, "This agent is paused: phone calls are not answered; browser tests still work." | 1. Open a published agent with a newer draft. 2. Test tab. 3. Read the card subtitle. | Low | Open | test-call-panel.tsx:62 always uses wizard.w5.call.subtitle (en.json:803). Branch on agent.published_version and agent.status === 'paused'; add keys to en.json and ar.json.
QA-074 | D11 | Audit log shows "–" for IP address on most actions | In Settings → Audit log only "Changed workspace settings" and "Created the workspace" show an IP. Published/paused/resumed an agent, took an agent live, added knowledge, invited someone, opened a ticket all show "–", although each was done from the same browser. Staff should be able to see where a change came from. | 1. Settings → Audit log. 2. Compare the IP column across rows. | Low | Open | Only the workspace routes pass the request IP into the audit row. AgentsService.audit() (agents.service.ts:~590-600) writes tenantId/actorUserId/meta and no ip; the knowledge, members (invite) and support writers do the same. Add ip to WorkspaceContext once in WorkspaceGuard and pass it from every audit() call; the column and the auditEntryResponse field already exist.
QA-075 | D10 | "1 numbers" / "1 calls": counts don't pluralise | Dashboard counters show "1 numbers" and "1 calls" when the count is 1. Expected: "1 number" / "1 call", "2 numbers" / "2 calls". | 1. Workspace with exactly one phone number → Home / Numbers card. 2. Agent or number with one call → "1 calls". | Low | Open | en.json:1527 "numbers": "{n} numbers" and en.json:1284 "count": "{n} calls" are plain strings. Use ICU plural: "{n, plural, one {# number} other {# numbers}}"; add the Arabic forms in ar.json (zero/one/two/few/many/other) so messages.test.ts passes.
QA-076 | D9 | Live page doesn't say the number is in a different area code than requested | A Toronto request (647) was given a 236 (BC) number because the requested code had no stock; the live page just shows the number with no note. The customer may not notice their "local" number isn't local. Expected: a one-line note on W7/live and the number's page: "No 647 numbers were available; we chose the closest, 236." | 1. W6 → request area code 647 (or 437). 2. Activate. 3. Live page shows a 236 number with no explanation. | Low | Open | purchase-attempts.ts records the code actually bought on the row; nothing surfaces it. Return requested_area_code and the bought code on phoneNumberResponse / the activation view, and show a note in onboarding/live/page.tsx and the D4 header when they differ. The W6 hint "We choose the closest available number" (en.json:929) covers the promise but not the outcome.

## Sheet2
Bug ID | Task | Title | Description | Steps | Priority | Status | Dev Comments
BUG-003 | D10 — Dashboard D1–D3 | Agent adds an extra "0" to an incomplete phone number instead of asking again | When the caller gives a phone number with a missing digit (9 digits), the agent pads it with a trailing 0 and saves it. Seen twice in one call: the caller said "8-7-6-5-4-3-2-1-0" and the agent recorded 876-543-2100. The wrong number was saved in both the reservation request and the staff message, so staff would call the wrong number. The agent should say the number looks incomplete and ask the caller to repeat it. Language en-IN, Standard tier, voice Hailey. | 1. Agents → Restaurant Reservations → Test → Start test call. 2. Say "Table for four this Friday at 7 PM, name Priya". 3. Give a 9-digit phone number: "8 7 6 5 4 3 2 1 0". 4. Check the agent's read-back and the phone number in Calls → the call → captured fields. | Medium | Open | BUG-003: Agent pads an incomplete phone number with "0" Speech recognition passed 9 digits correctly ("Eight seven, six, five, four. Three. Two. One. Zero." in the transcript). The model then reformatted the number to North American XXX-XXX-XXXX and invented a trailing 0 (876-543-2100). The wrong number was stored in the captured fields and in the staff message. Root cause: the script skeleton has no rule for validating numbers. "Confirm captured details back to the caller before ending" (agent-stack-v1.ts line 116 / prompt-builder.ts APPENDIX_B_SKELETON) doesn't tell the model never to fill in missing digits. Suggested fix: - Add to the §9.4 guardrails or the skeleton Rules: "Never add, remove or guess digits in a phone number. If it is not 10 digits, say how many you heard and ask the caller to repeat it. Read the number back digit by digit." - Optional: digit-count validation on the captured phone field in the post-call analysis. Evidence: browser test call, 426 s, 26 Oct, Spice Garden / Restaurant Reservations draft v2, en-IN, Standard.
BUG-004 | D10 — Dashboard D1–D3 | Agent says "Thank you for calling" in the middle of the conversation | The agent ends ordinary answers with the closing line while the caller is still talking. Examples: after the reservation read-back it said "…This is a request until the restaurant confirms availability. Thank you for calling Spice Garden Restaurant." without asking "anything else?", and the caller had to say "No, wait". On an earlier call it added "Thank you for calling" after the Saturday hours and parking answers. The call continues, but the caller thinks it's ending. The closing line should be used only when the caller says they're done. | The agent ends ordinary answers with the closing line while the caller is still talking. Examples: after the reservation read-back it said "…This is a request until the restaurant confirms availability. Thank you for calling Spice Garden Restaurant." without asking "anything else?", and the caller had to say "No, wait". On an earlier call it added "Thank you for calling" after the Saturday hours and parking answers. The call continues, but the caller thinks it's ending. The closing line should be used only when the caller says they're done. | Medium | Open | BUG-004: "Thank you for calling" said mid-conversation The closing line is spoken after ordinary answers (hours, parking, the reservation read-back) while the caller is still talking. Root cause: - Skeleton "## Ending\n{closing_line}" (agent-stack-v1.ts line 126) gives the closing sentence with no condition for when to say it. - The end_call tool description is just "End the call when the conversation is over." (retell.gateway.ts line 85) and doesn't define when that is. Suggested fix: - Skeleton Ending: "After each answer ask 'Is there anything else I can help you with?'. Say {closing_line} and use end_call only after the caller confirms they need nothing else or says goodbye." - end_call description: "Use only after the caller has said they need nothing else or has said goodbye. Never end after answering a question." QA is testing whether adding the same instruction to Brief → "Anything else" plus Regenerate works around it. Result to follow.
BUG-005 | D10 — Dashboard D1–D3 | Agent reads the staff transfer phone number aloud to the caller | When offering or retrying a transfer, the agent says the private staff number, e.g. "Shall I transfer you now to +919003172279?" (first call) and "would you like me to try the transfer again to…" (second call; the caller interrupted). Callers should hear "transfer you to our staff", never the internal number. The number is in the transfer tool description ("Transfer the caller to {number}…", backend/api/src/modules/retell/retell.gateway.ts line 89) and in the generated script's hand-off section, so the model repeats it. | 1. Brief → hand-off rule "party larger than 10 → Transfer the call" with a transfer number. 2. Test → Start test call. 3. Say "I need a table for fifteen people". 4. Listen when the agent offers or retries the transfer. | Medium | Open | BUG-005: Staff transfer number read aloud to callers The agent says "Shall I transfer you now to +919003172279?" (call 1) and "try the transfer again to…" (call 2). Root cause: the number is in the model's context in two places: - the transfer tool description: `Transfer the caller to ${number} when they ask for a person.` (retell.gateway.ts line 89) - the generated script Hand-off: briefForModel() emits "{condition} → transfer to {transfer_number}" (prompt-builder.ts line 326), and the skeleton "use transfer to {transfer_targets}" Suggested fix: - Tool description without the number, e.g. `Transfer the caller to ${label ?? 'a staff member'}…` (the number is already in transfer_destination). - Use the target's name or label in the brief/script instead of the E.164. - Guardrail: "Never say a transfer or staff phone number to the caller."
BUG-006 | D10 — Dashboard D1–D3 | Test tab suggests "Ask for staff", but transfers cannot work in a browser test call | The Test tab's "Try saying" list includes "Can I speak to someone at the restaurant directly?" and "I need a table for 15 people", both of which trigger a transfer. Browser test calls can't transfer to a phone (the call summary says "Transfers to staff failed due to the web call"), so the agent says "the transfer didn't go through" repeatedly. The customer will think transfers are broken. Expected: hide transfer suggestions in browser tests, or show "Transfers work on real phone calls only". | 1. Agents → Restaurant Reservations → Test. 2. Start test call and say "Can I speak to someone at the restaurant directly?" 3. Agent tries to transfer → "Sorry—the transfer didn't go through." 4. Open the call in Calls → the summary mentions the web-call transfer failure. | Low | Open | BUG-006: Test tab "Try saying" suggests transfer scenarios that cannot work in a browser test The test panel shows the first 4 generated scenarios (draft.scenarios.slice(0, 4), frontend/web/src/components/wizard/test-call-panel.tsx lines 107–117). For this agent they include "Large party" and "Ask for staff", which trigger transfer_call. A web call cannot transfer to a phone, so the agent says "the transfer didn't go through" repeatedly. The call summary even says "Transfers to staff failed due to the web call". Suggested fix (any one): - Filter out scenarios that lead to a transfer in the browser panel, or mark them "works on phone calls only". - Show a note in the test panel: "Transfers can't be tested in the browser." - Generation: tag scenarios with the action they exercise so the panel can filter them.
BUG-007 | D10 — Dashboard D1–D3 | Agent reads out the whole menu list in one answer | Asked "Vegetarian dishes?", the agent read 20 items with prices in one reply, including non-dishes (Coffee, Soft Drink, Sparkling Water, Masala Chai). That's too long for a phone call and breaks the script's own rule "Keep answers under 2 sentences unless asked for detail". Expected: 3–4 examples, then "Would you like to hear more?" | 1. Agent with a restaurant menu PDF uploaded. 2. Test → Start test call. 3. Ask "What vegetarian dishes do you have?" 4. Observe the length of the reply. | Low | Open | BUG-007: Agent lists the whole menu in one answer "Vegetarian dishes?" → the agent read 20 items with prices, including drinks (Coffee, Soft Drink, Sparkling Water). The skeleton rule "Keep answers under 2 sentences unless asked for detail" (agent-stack-v1.ts line 121) isn't strong enough against the menu knowledge source / brief.documents, which is attached verbatim. Suggested fix: add to the skeleton Rules, or to knowledgeSection() for the menu role: "When asked for a category, name at most 3–4 items and offer to tell more. Never read the full menu."
BUG-008 | D8 | Invite link is lost when the invitee is not signed in: lands on "Set up your workspace" instead of "Join workspace" | When an invited user opens the invite link while signed out, they are sent to login with ?next=/invite/?token=…. After sign-in (Google), the portal ignores next and runs the home redirect; a new user with no workspace is sent to /setup/workspace/. The invite is never accepted and stays "Pending" in Settings → Team. The same link opened while already signed in shows "Join workspace → Accept invitation" correctly, so only the return-after-login step is broken. Code: auth-provider.tsx:149 only updates the URL; app/page.tsx:23 redirects over it; guards.tsx:166 ignores next. Risk: invitees create their own empty workspace instead of joining the team. | 1. Owner: Settings → Team → invite tqa7726@gmail.com as Viewer → copy link. 2. Open an Incognito window (signed out). 3. Paste the invite link → login page. 4. Sign in with Google as tqa7726@gmail.com. 5. Actual: "Set up your workspace"; the invite is still Pending. 6. Paste the invite link again while signed in → "Join workspace" appears (expected on step 4). | High | Open | Invite flow: QA findings on staging, 26 Oct (tqa7726@gmail.com, Incognito, Google sign-in) 1. Invite link lost when the invitee isn't signed in (High, BUG-008 / #1) Signed out → /invite/?token=… → /login/?next=… → sign in → /setup/workspace/. The invite stays Pending. The same link while signed in shows "Join workspace → Accept invitation" correctly. Cause: auth-provider.tsx:149 only replaceState()s to returnTo, then app/page.tsx:23 useSessionGate('/') redirects a no-workspace user to /setup/workspace/; guards.tsx:166 ignores ?next=. Fix: router.replace(returnTo) after the callback and skip the root gate when returnTo exists (same-origin only); honour ?next= in RedirectIfSignedIn; carry next through /signup and /verify-email (#2, #3). 2. No invite email is sent, but the button says "Send invite" (Medium) POST /invites (members.service.ts ~185–235) only returns the token; there is no outbox or notification. The invitee received nothing. Please confirm with Pramod: either email the link through the outbox (dedupe on invite id), or rename the button to "Create invite link" and say no email is sent. 3. Join screen doesn't show workspace, role or inviter (Low) "You have been invited to a workspace…" (en.json auth.invite.body). There is no GET for an invite by token. Suggested: public GET /invites/:token/preview → {workspace_name, role, invited_by_name, expires_at}. 4. A4 setup: time zone defaults to the browser's, not the country (Low) setup/workspace/page.tsx:53 → Country = Canada with Time zone = Asia/Calcutta. Hours, the digest and day windows then run on India time. Default to the country's main zone (CA → America/Toronto) or warn when they don't match.
BUG-009 | D11 | Table headers are centred while the values are left-aligned (Pending invitations and other dashboard tables) | In Settings → Team → Pending invitations, the headers Email / Role / Expires are centred but the values are left-aligned, so the columns don't line up. The same table component renders most dashboard lists, so other tables are likely affected. | 1. Settings → Team. 2. Invite any email so a pending row exists. 3. Look at Pending invitations: headers are centred over left-aligned values. 4. Check Members, Numbers, Wallet ledger and Audit log for the same problem. | Low | Open | frontend/web/src/components/dashboard/data-table.tsx:76: the <th> class only adds text-right / text-center when align is set; with no align it gets nothing, so the browser's default th { text-align: center } wins over the text-left on <table> (line 72), because th doesn't inherit it. Fix: add text-left as the default on <th> (e.g. c.align === 'right' ? 'text-right' : c.align === 'center' ? 'text-center' : 'text-left'). One-line change that fixes every DataTable; check D2/D3's own tables for the same.
BUG-010 | D11 | Pending invitations has no status, and expired invites still show as pending | The Pending invitations table has no Status column. Expired invites stay under "Pending invitations" looking valid while their link no longer works. Expected: a Status column (Pending / Expired), expired rows marked, and a "Resend" action for expired invites. | 1. Settings → Team → invite someone. 2. Note the Expires date (7 days). 3. After that date (or with expires_at set in the past on a test row), open Settings → Team. 4. The row is still under "Pending invitations" with no Expired status. | Medium | Open | API: listInvites() (backend/api/src/modules/workspaces/members.service.ts:240-243) filters only acceptedAt: null, never expiresAt. Fix: add status: 'pending' ¦ 'expired' (from expires_at < now()) to inviteResponse in @portal/schemas, regenerate OpenAPI and the client. UI: frontend/web/src/components/dashboard/settings/team-tab.tsx, invite columns: add a Status column (Badge: Pending / Expired), and for expired rows show "Resend", which calls the existing POST /invites (re-invite already replaces the token). Optionally, a cleanup in the scheduled jobs for invites expired more than 30 days.
BUG-016 | D8 | After "Sign out" on a wrong-email invite, Google signs the same account back in, with no way to pick the invited one | The invite page says the invite was sent to a different address and offers Sign out. After signing out, "Continue with Google" goes straight back in as the same Google account (tqa7726@gmail.com) with no account picker. The user lands on the same error and can't switch to skytest411@gmail.com without signing out of Google itself or closing the browser. | 1. Bright Smile → Settings → Team → invite skytest411@gmail.com as Viewer, copy the link. 2. In Incognito, signed in as tqa7726@gmail.com (Google), open the link → "sent to a different email" error. 3. Click Sign out. 4. Sign in → Continue with Google. 5. Actual: signed in again as tqa7726 with the same error. Expected: Google's account picker appears so skytest411 can be chosen. | Medium | Open | auth-provider.tsx:217-228: logout() ends the Auth0 session only (client().logout({ returnTo })). The Google session stays, and login() (auth-provider.tsx:196-209) sends no prompt, so Google auto-selects the signed-in account. The invite page's Sign out (invite/page.tsx:131-140) is the case where a different account is the whole point. Suggested fix: after a sign-out from the invite page, call login with authorizationParams.prompt = 'select_account' (Google shows its account picker), or prompt: 'login'. Remember a "switch account" flag next to pendingInvite so the next login carries it.